## Punch List
AI Freedom Studios — Duane ¦ Project Punch List
Build 6 (final, delivered for testing) — live at https://aifreedomstudios.com ¦ Stack: React 18 · Vite 6 · Base44 SDK · Tailwind · Radix UI
# | Category | Work Item | Status | Notes
Phase 1 — Platform Foundation & Setup
1 | Foundation | Base44 React SPA scaffold (Vite 6, React 18, Tailwind, Radix UI) | Complete | Built on Base44 managed backend — no custom server required.
2 | Foundation | 138 page components (full app surface) | Complete | Dashboards, studios, admin, agency/white-label, billing, analytics, etc.
3 | Foundation | 170+ reusable UI components | Complete | Modular component library across all modules.
4 | Foundation | 205 data entities (schemas) | Complete | Clients, projects, campaigns, social, leads, production, etc.
5 | Foundation | Authentication (Base44 SDK login/logout/token) | Complete | base44.auth — login, redirect, session handling.
6 | Foundation | Routing — public + authenticated routes (React Router) | Complete | Includes role-based access (user vs admin/super-admin).
7 | Foundation | Repo, README, .gitignore, env templates | Complete | Documented setup + environment variables.
8 | Foundation | Deployment config (nginx.conf, deploy.sh, .env.example) | Complete | One-command VPS deploy script + nginx config.
Phase 2 — Video & Content Studio
9 | Studio | Video Studio (model catalog, preview rails, settings, library) | Complete | Modular video generation studio; Runway-generated video verified live.
10 | Studio | YouTube Studio (connect, file upload, analytics) | Complete | Direct file upload + URL; environment-aware OAuth redirect.
11 | Studio | AI Copilot & content tooling (scripts, captions, ideas) | Complete | Claude-powered content generation.
12 | Studio | Double-Layout routing bug fix | Complete | Removed duplicate layout wrapping across ~13 pages.
Phase 3 — Social Media Integrations
13 | Social | Twitter / X (OAuth 2.0 PKCE, post, profile) | Complete | Connected. Live posting requires paid X API tier (client to enable).
14 | Social | LinkedIn (auth, post, analytics) | Complete | Verified posting live during demo.
15 | Social | Facebook (auth, post) | Complete | Verified posting live during demo.
16 | Social | Instagram / Meta (auth, post) | Complete | Verified posting live during demo.
17 | Social | TikTok (OAuth PKCE, post) | Complete | Built & connected; TikTok app approval pending on platform side.
18 | Social | YouTube publishing | Complete | Verified upload live during demo.
19 | Social | OAuth security hardening | Complete | Removed hardcoded fallback secret; all functions gated on auth.
Phase 4 — Scheduling & Automation
20 | Automation | Scheduled auto-publishing (FB, IG, YouTube, LinkedIn) | Complete | Background worker runs every 5 min (Base44 5-min minimum).
21 | Automation | Immediate + scheduled posting (createScheduledPost / publishSocialPost) | Complete | Timezone-aware (local -> UTC); double-publish guard.
22 | Automation | Content calendar & approved-content publishing | Complete | Approval queue -> auto-publish pipeline.
Phase 5 — AI Agents (multi-agent layer)
23 | Agents | ARIA — AI Executive Assistant | Complete | Daily briefings, business intelligence on real entity data.
24 | Agents | Social & Content Agent | Complete | Drafts, schedules & publishes across all platforms.
25 | Agents | Campaign & Ads Agent | Complete | Campaigns, budgets, ROAS, ad creatives.
26 | Agents | Sales & Leads Agent | Complete | Lead scoring, pipeline, follow-ups (native).
27 | Agents | Production Agent | Complete | Production queue, render jobs, scripts, projects.
28 | Agents | Master Copilot — orchestrator / hierarchy | Complete | Single command center delegates to all specialist agents (delegateToAgent).
29 | Agents | Agent design — Claude Sonnet 4.6, scoped tools, memory | Complete | Least-privilege entity access per agent; memory enabled.
Phase 6 — Native Leads & Sales (replaced GoHighLevel)
30 | Leads | GoHighLevel dependency removed | Complete | Connect/proxy removed; a few residual GHL entities/lead-magnet channel still to be cleaned.
31 | Leads | LeadActivity entity + activity timeline | Complete | Append-only history of every lead touch.
32 | Leads | Lead scoring (autoScoreNewLead + AI scoreLead, 0-100) | Complete | Auto-scores new leads; AI reasoning stored.
33 | Leads | Pipeline stages + updateLeadStage | Complete | new -> contacted -> qualified -> nurture -> won/lost/spam.
34 | Leads | Follow-up automation (sendFollowUpSequence) | Complete | Sequenced multi-channel follow-ups.
35 | Leads | convertLeadToClient | Complete | Won lead -> Client conversion.
36 | Leads | Contact form + submitContactForm (lead capture) | Complete | Public lead capture into native pipeline.
Phase 7 — Voice (VAPI)
37 | Voice | VAPI voice-to-voice (vapiAssistant, vapiToolHandler, VapiVoiceButton) | Complete | Voice on AI Copilot; assistant auto-provisioned. Requires VAPI keys.
Phase 8 — Deployment & Go-Live
38 | Deploy | Production domain live — aifreedomstudios.com | Complete | Live on client domain (Hostinger/Base44).
39 | Deploy | SSL / HTTPS | Complete | Secured.
40 | Deploy | Build verified (compiles clean) | Complete | Production build verified at each milestone.